| User Testing Strategy Partner Integration Program — TL;DR | April 2026 Director of Design |
| --- | --- |

THE GOAL

Map user testing across two partner integrations to validate our onboarding, assessment, and personalization experience — using moderated sessions via User Interviews, qualitative synthesis, and a phased beta rollout — while protecting member PHI/PII and keeping partners in the loop.

| Partner 1 — Handoff Journey - Enters from partner app via a CTA - Assessment pre-filled with partner data - Personalized recs on first session - Guided to care manager for 1:1 support - Unique rewards only inside our experience Test focus: Does the pre-fill feel helpful vs. invasive? Is the handoff seamless? | Partner 2 — White-Label Standalone - Comes directly to our white-labeled app - Full assessment — starts from zero - Complete personalized product/service/article list - Boosted rewards reflecting higher monetary value Test focus: Is starting from zero overwhelming? Do boosted rewards drive completion? |
| --- | --- |

WHAT WE MEASURE — 8 EVALUATION DIMENSIONS

| Compelling | Seamless | Trustworthy | Useful | Meets Expectations | Return-Worthy | Recommend | Feels Understood |
| --- | --- | --- | --- | --- | --- | --- | --- |

| HOW WE TEST Moderated 8–10 participants / partner · 60 min · User Interviews · Live with partner observer seat Unmoderated 50+ participants / partner · 15–25 min · Async tasks · Scale + completion rates Partner observes Silent observer seat · Post-session debrief · No PHI/PII collected · Synthetic data only | HOW WE RECRUIT - In-app intercept — triggered after meaningful action (not first open) - Campaign outreach — targeted email/push coordinated with partner - Care manager referral — nominated power users + edge cases |
| --- | --- |

QUALITATIVE → DESIGN PIPELINE

| 1 Session Capture | 2 Team Debrief | 3 Affinity Mapping | 4 Insight Extraction | 5 Design Implication | 6 Decision Log | 7 Partner Report |
| --- | --- | --- | --- | --- | --- | --- |

Sessions → 24hr debrief → affinity map (Miro) → insight statements → design recommendations → decision log → partner report (5 business days)

| BETA ROLLOUT Phase; %; Go Criteria. Soft Launch; ~5%; No critical blockers · Design sign-off · Partner approved. Expanded Beta; ~20%; Stable for 2 weeks · Synthesis complete · No new P1 bugs. Full Rollout; 100%; Stable 2–4 weeks · All priority changes shipped · Partner sign-off. | LONGITUDINAL TOUCHPOINTS Day 7; In-app 3-question micro-survey · Early retention signal. Day 30; Email survey + optional 30-min follow-up call · Care manager NPS. Day 90; Cohort analysis + 5 depth interviews · Long-term outcome signal. |
| --- | --- |

NEXT STEPS

| This week | Build Miro board (10-row structure) · Confirm legal review of consent language |
| --- | --- |
| Week 1–2 | Align screener criteria with partners · Set up User Interviews · Draft discussion guides |
| Week 2 | Launch recruitment across all 3 channels simultaneously |
| Week 3–4 | Run moderated session series with partner debrief after each session |
| Week 4–5 | Affinity mapping synthesis · Deliver insight report to partners |
| Week 6+ | Ship design changes · Initiate 5% soft launch |

Full strategy document available for detailed methodology, screener criteria, and partner observation protocol.